## Sheet1
Digital Project Gantt Chart
Week Commencing | 2005-02-07 | 2005-02-14 | 2005-02-21 | 2005-02-28 | 2005-03-07 | 2005-03-14 | 2005-03-21 | 2005-03-28 | 2005-04-04 | 2005-04-11 | 2005-04-18 | 2005-04-25 | 2005-05-02 | 2005-05-09 | 2005-05-16 | 2005-05-23 | 2005-05-30 | 2005-06-06 | (End of term)
Introduction week | bar: 2005-02-07
Planning of Gantt Chart | bar: 2005-02-07
Modular Breakdown of Sections | bar: 2005-02-14
Generating Detailed Specifications | bar: 2005-02-14 to 2005-02-21
Generating Top-Down Block Diags | bar: 2005-02-14 to 2005-02-21
Design Blocks: Clock | bar: 2005-02-21
Design Blocks: Switch | bar: 2005-02-21
Design Blocks: LED interfacing | bar: 2005-02-21
Design Blocks: Bin to Gray Decoder | bar: 2005-02-21
Design Blocks: Counter Desgin (5b) | bar: 2005-02-21 to 2005-02-28
Design Blocks: Edge Triggered Logic | bar: 2005-02-21 to 2005-02-28
Simulation of Design | bar: 2005-02-14 to 2005-03-07
Conversion to PCB layout | bar: 2005-02-28 to 2005-03-14
Budgeting / Buying Components | bar: 2005-02-21 to 2005-03-14
Get PCB made | bar: 2005-03-14
Build/Test Clock Circuit | bar: 2005-03-21
Build/Test Push Switch Input | bar: 2005-03-21
Build/Test LED outputs | bar: 2005-03-21 to 2005-03-28
Build/Test Gray Code Converter | bar: 2005-03-28 to 2005-04-04
Build/Test 5 bit counter | bar: 2005-04-04 to 2005-04-18
Build/Test Edge Triggered Logic Block | bar: 2005-04-11 to 2005-04-25
Test the circuit as a whole | bar: 2005-04-18 to 2005-05-02
Build the Components into the box | bar: 2005-03-21 to 2005-05-02
Demonstration | bar: 2005-05-09
Key | 2005-02-14: Planned time
Actual Time Spent
| Deadlines | [8 empty] | Week |  | Date | [5 empty] | # Marks
| Block Diagram viva voce | [8 empty] | 3 |  | Friday 4th March 05 | [5 empty] | 10
| Combi block design (report) | [8 empty] | 5 |  | Thurs 17th March 05 | [5 empty] | 30
| Full Design Simulation Demo | [8 empty] | 7 |  | Friday 15th April 05 | [5 empty] | 30
| Hardware Demo (+L/B submtd) | [8 empty] | 11 |  | Friday 13th May 05 | [5 empty] | 30